## Existing OSL updt costs 10.2021
*The data contained within this spreadsheet is shared under an Open Government Licence - City of Calgary. This open government licence only applies to this data and this data only. Terms of Use can be found at https://data.calgary.ca/stories/s/Open-Calgary-Terms-of-Use/u45n-7awa | [10 empty] | Past Actual Spend | [7 empty] | Cost Projection (not include Admin) | [7 empty] | Cost Projections Total
Name in 2016 or 2018 Bylaw | Project Name | Utility | Type | Current Project / Budget Activity Status (November 2021) | Current Detailed Status (November 2021) | Current Cost Projection Classification | Estimated Construction Completion (substantial) | Project notes - Nov. 18, 2021 | Original 2015 Cost Estimate (Source: Levy Bylaw 2016/2018) Forecasted Total Project Cost (10-Year time Horizon 2015-2024) | Original OSL Rate Estimate (forecasted annual spends 2015-2020) | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Past Actual Spend (2015-2020) Source: Annual Budget Report | VARIANCE Original Levy projections to Actuals (2015-2020) | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 |  | Recommended Projection for Levy Rate
Sanitary Upgrade Infrastructure | Sanitary Upgrade Infrastructure
Shouldice Trunk Upgrade | Shouldice Trunk Upgrade | Sanitary | Linear Upgrade | Hold | Feasibility / Scoping | Class 5 | 2026-07-02 | Proactively deferred significantly to match pace of growth and timing of when project is needed. Another driving factor for deferring this project was to address financial shortfalls. | 24000000 | 23942000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 23942000 | 0 | 0 | 4800000 | 5000000 | 5000000 | 4500000 | 0 | 0 | 19300000 | 19300000
Nose Creek Trunk Upgrade | Nose Creek Trunk Upgrade | Sanitary | Linear Upgrade | Active | Phased -- construction & Design | Class 2 | 2023-12-31 | Split into 2 phases: Phase A - complete in 2011. Phase B - ongoing - Portion of it is complete (Contract 2 - completed 2012-2014 and contracts 1,3, and 5 - completed 2015-2020). Contract 4 (only outstanding for Phase 2) to be completed in 2023. | 87700000 | 87669000 | 8103566 | 13350671.1624 | 2020533.9386 | 757172.0271 | 3506443.1555 | 290803.3339 | 28029189.6175 | 59639810.3825 | 813717.79 | 0 | 42700000 | 0 | 0 | 0 | 0 | 0 | 43513717.79 | 43513717.79
Inglewood Trunk Upgrade | Inglewood Trunk Upgrade | Sanitary | Linear Upgrade | Active | Construction | Class 1 | Phase 1: 16-Nov-20 Phase 2: 30-Apr-24 | Phase 1 (south of the Bow River)- complete, Phase 2 (crossing the Bow River) - 2024. Large variance primarily due to significant mobilization/demobilization costs and supply and installation of tunnelled pipe. Scope adjustments also required due to insufficient room to connect trunk to existing 15 Street S sanitary trunk (instead needed to connect to Inner City Trunk and a second siphon became necessary). | 55900000 | 55880000 | 940311 | 2169952.8414 | 542334.4279 | 1679607.6716 | 51637806.1129 | 23849692.6808 | 80819704.7346 | -24939704.7346 | 987708 | 110274 | 10740000 | 8460000 | 0 | 0 | 0 | 0 | 20297982 | 20297982
McKenzie Siphon Upgrade | McKenzie Siphon Upgrade | Sanitary | Linear Upgrade | Active | Design | Class 5 | 2022 | Detailed design ongoing, RFx (Request For X) scheduled December 2021. Construction due to start March 2022. | 7400000 | 7382000 |  | 0 | 0 | 0 | 0 | 208732.734 | 208732.734 | 7173267.266 | 500140.23 | 9790567 | 0 | 0 | 0 | 0 | 0 | 0 | 10290707.23 | 10290707.23
Water Upgrade Infrastructure | Water Upgrade Infrastructure
South Glenmore Reservoir Basin II | South Glenmore Reservoir Basin II | Water | Facility | Hold | Design | Class 5 | TBD | Project on hold. | 40400000 | 33840000 | 72545 | 47533.8086 | 0 | 0 | 0 | 0 | 120078.8086 | 33719921.1914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bearspaw Pump Station STN012 Upgrade | Bearspaw Pump Station STN012 Upgrade | Water | Facility | Active | Design | Class 3 | 2022-12-31 | Bearspaw Pump Station STN020 Upgrade merged with this project resulting in a slight increase to the most recent estimate but an overall savings for the Utility and Industry (increased efficiency). Scope changed to include 3 new pumps. | 6600000 | 6556000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6556000 | 1879030.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879030.41 | 1879030.41
Bearspaw Pump Station STN020 Upgrade | Bearspaw Pump Station STN020 Upgrade | Water | Facility |  |  |  |  | Merged with Bearspaw Pump Station STN012 Upgrade. | 2000000 | 1979000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1979000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nose Hill Feedermain | North Calgary Water Servicing Strategy (Previously Nose Hill Feedermain) Nose Hill Feedermain Macewan Pump Station STN057 Beddington Cross Tie | Water | Linear Upgrade | Active | Design | Class 3 | 2026-06-01 | Project scope changed significantly - updated estimate included. Was called "Nose Hill Feedermain" but now has become the North Calgary Water Servicing Strategy (NCWSS). Investigation of options in progress due to changing growth patterns. Options currently under exploration and preliminary design underway. More information will be shared in future. Current design is for new feedermain to be tunelled under Nose Hill, then combination of open-cut and microtunneling for rest of route to Beddington Reservoir. Project on-hold until exploration of options and decision is made. A new calculation for benefit allocation will need to be completed due to the changing growth patterns and signifcant change in scope. | 37800000 | 37781000 | 219847 | 30981.2972 | 2356508.2601 | 515341.1464 | 887672.3892 | 1834281.6642 | 5844631.7571 | 31936368.2429 | 29262348 | 60192271 | 49015245 | 30998390 | 938754 | 100000 | 0 | 0 | 170507008 | 170507008
Country Hills Blvd Uptown Feedermain | Country Hills Blvd.Feedermain | Water | Linear Upgrade | Hold | Feasibility / Scoping | Class 5 | TBD | Latest estimate $31.5M. Project on hold. Investigating deferral and removal from OSL project list until a future bylaw. | 29800000 | 28858000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 28858000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 291600000 | 283887000 | 9336269 | 15599139.1096 | 4919376.6266 | 2952120.845 | 56031921.6577 | 26183510.4128 | 115022337.6517 | 168864662.3483 | 33442944.43 | 70093112 | 107255245 | 44458390 | 5938754 | 4600000 | 0 | 0 | 265788445.43

## Completed Upgrade projects
*The data contained within this spreadsheet is shared under an Open Government Licence - City of Calgary. This open government licence only applies to this data and this data only. Terms of Use can be found at https://data.calgary.ca/stories/s/Open-Calgary-Terms-of-Use/u45n-7awa
Name in 2016 or 2018 Bylaw | Project Name | Utility | Type | Estimated Construction Completion (substantial) | Project notes - Nov. 18, 2021 | Original 2015 Cost Estimate (Source: Levy Bylaw 2016/2018) Forecasted Total Project Cost (10-Year time Horizon 2015-2024) | Original OSL Rate Estimate (forecasted annual spends 2015-2020) | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Past Actual Spend (2015-2020) Source: Annual Budget Report | VARIANCE Original Levy projections to Actuals (2015-2019) | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Sanitary Upgrade Infrastructure | Sanitary Upgrade Infrastructure
Saddle Ridge Sanitary Upgrade | Saddle Ridge Sanitary Upgrade (Relief Sewer) | Sanitary | Linear Upgrade | Complete | Project complete | 5100000 | 5110000 | 167043 | 5232280.6839 | 719066.0576 | 10590.1279 | 0 | 9650.5044 | 6138630.3737 | -1028630.3737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bowness Trunk Upgrade | Bowness Offload Trunk Upgrade | Sanitary | Linear Upgrade | Complete | During detailed design phase we were able to simplify the route for the trunk, based on the selection of microtunneling as the construction method over the original concept of open-cut trenching. Yielded an approx. saving of $6M. | 48600000 | 35150000 | 30017739 | 3469030.9355 | 5070.3183 | - | 48861.8299 | - | 33540702.0838 | 1609297.9162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Water Upgrade Infrastructure | Water Upgrade Infrastructure
Airdrie FM Tie-in and Meter Chamber Relocation | Airdrie FM Tie-in and Meter Chamber Relocation (NE Transit and Utility Corridor Feedermain Phase 2) | Water | Facility | Complete | Completed in 2017. Meter moved to allow greenfield development. Airdrie meter moved outside of city limits to just measure regional flow. | 1400000 | 1425000 | 185335 | 715415.5551 | 617316.2302 | 187796.87 | 0 | 0 | 1705863.6553 | -280863.6553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pump Station 36 Installation | Pump Station 36 Installation | Water | Facility | Complete | This project is part of the solution for the North Calgary Water Servicing Strategy. Completed in 2016-2017. Supports both greenfield and established areas. | 200000 | 222000 |  | 470185.7623 | 54588.5883 | 0 | 0 | 0 | 524774.3505 | -302774.3505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 55300000 | 41907000 | 30370117 | 9886912.9368 | 1396041.1943 | 198386.9979 | 48861.8299 | 9650.5044 | 41909970.4633 | -2970.4633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0