## Linear Extension Details
Off-site Levy Linear Extension Projects. Updated November 18, 2021
*The data contained within this spreadsheet is shared under an Open Government Licence - City of Calgary. This open government licence only applies to this data and this data only. Terms of Use can be found at https://data.calgary.ca/stories/s/Open-Calgary-Terms-of-Use/u45n-7awa | [10 empty] | Past Actual Spend (include Admin) | [7 empty] | Cost Projection (not include Admin)
Project Name (Edited with Brief Description) | Name in 2016 or 2018 Bylaw | Utility | Type | Current Project / Budget Activity Status (Oct 2021) | Current Detailed Status (Oct 2021) | Current Cost Projection Classification (Oct 2021) | Estimated Construction Completion (substantial) | Project notes - Nov. 18, 2021 | Original 2015 Cost Estimate (Source: Levy Bylaw 2016/2018) Forecasted Total Project Cost (10-Year time Horizon 2015-2024) | Original OSL Rate Estimate (forecasted annual spends 2015-2020) | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Past Actual Spend (2015-2020) |  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Cost Projections Total | Recommended Projection for Levy Rate
Sanitary Linear Extension Infrastructure
Seton Tunnel P H 1 (Rangeview Sanitary Trunk) & Rangeview Sanitary Trunk Laterals (Phase 1) Rangeview Sanitary Trunk Phase 1 (Tunnel + Open-Cut) | Seton Tunnel Ph 1 | Sanitary | Linear Extension | Active | Maintenance period | Class 1 | 2021 | Seton Tunnel Ph 1 scope includes connection at Cranston, East into Rangeview, up to 52nd Street. Work completed was based on tenders in 2018 and 2019, including complex mircotunnelling and earthworks. Costs associated with original levy calculations were based on Class 5 Estimates. Difference in spend was due to difference between Class 5 estimate and actual tender pricing. For future work, looking to bundle storm and sanitary to construct at the same time, for cost savings. Construction is complete, project is now in the maintenance period. | 31800000 | 17689000 |  | 112172.305 | 1255530.176 | 2422190.2833 | 4249803.6872 | 30471052.7843 | 38510749.2359 |  | 6765498.6 | 1884996 | 0 | 0 | 0 | 0 | 0 | 0 | 8650494.6 | 8650494.6
Rangeview Sanitary Trunk Laterals | Rangeview Sanitary Trunk Laterals | Sanitary | Linear Extension | Cancelled | Project Bundled with Other |  | N/A | Scope and total cost now included in Rangeview Sanitary Trunk Phase 2 Lateral 1 and Rangeview Sanitary Trunk Phase 2 Lateral 2. | 7000000 | [7 empty] | 0 | [9 empty] | 0 | 0
Rangeview Sanitary Trunk Phase 2 Lateral 1 only (52 ST/77 ST SE) | Rangeview Sanitary Trunk Laterals | Sanitary | Linear Extension | Active | Construction | Class 1 | Dec. 2021 | Original project, listed as 'Seton Tunnel Ph 2' in the Off-site levy bylaw, split into 2 projects. This portion advanced to align with storm trunk construction in 2021 to increase efficiencies/reduce cost. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 4400000 | 4000000 | 0 | 6899000 | 0 | 0 | 0 | 0 | 15299000 | 15299000
Rangeview Sanitary Trunk Ph 2: Seton Tunnel PH 2 & Rangeview Sanitary Trunk Lateral (Ph 2 Lateral 2 at 88 ST SE) - May be renamed as Rangeview Sanitary Phase 3 | Seton Tunnel Ph 2 | Sanitary | Linear Extension | Hold | Hold | Class 5 | 2025 or Beyond | Original project, listed as 'Seton Tunnel Ph 2' in the Off-site levy bylaw, split into 2 projects. | 18800000 | 2815000 | [6 empty] | 0 |  | 2027: 6726000; 2028: 6726000 | 13452000 | 13452000
Belvedere Sanitary Trunk – East Basin | Belvedere Sanitary Trunk | Sanitary | Linear Extension | Active | Design | Class 4 | 2023 | Draft Construction Agreement (CA) pending acceptance by the developer. Construction timing could change pending resolution and timing of executed CA. | 6000000 | 6000000 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 344421.5 | 6742578 | 0 | 0 | 0 | 0 | 0 | 0 | 7086999.5 | 7086999.5
Glacier Ridge East Basin Sanitary Trunk | Glacier Ridge East Basin Sanitary Trunk | Sanitary | Linear Extension | Active | Design | Class 1 | 2022 | Future sections are dependent upon right-of-way from Brookfield. 2021 project estimates are dependent on right of way and alignment finalization. Deep excavation and challenging earthworks considerations. | 4010000 | 4010000 |  | 0 | 0 | 0 | 52639.9121 | 1532388.1915 | 1585028.1036 |  | 2688046.86 | 6316000 | 0 | 0 | 0 | 0 | 0 | 0 | 9004046.86 | 9004046.86
Glacier Ridge West Basin Sanitary Trunk: Phase 1 (144 AV NW to future Shaganappi) Phase 2 (future Shaganappi to 69 ST NW) | Glacier Ridge West Basin Sanitary Trunk | Sanitary | Linear Extension | Active | Design | Class 2 | 2022 | Split into 2 phases | 8170000 | 3000000 |  | 0 | 0 | 0 | 93256.4189 | 151404.8959 | 244661.3147 |  | 2483968.36 | 14678820 | 0 | 0 | 0 | 0 | 0 | 0 | 17162788.36 | 17162788.36
Water Linear Extension Infrastructure
Rangeview Ogden Feeder Main Phase 1 | Ogden Feeder Main | Water | Linear Extension | Active | Design | Class 1 | 2022 | Feedermain now split into two phases. Phase 1 is in preliminary design, Phase 2 is in Detailed Design. Project was deferred due to budget constraints. Total cost of full scope will exceed original estimate. | 38500000 | 20244000 |  | 0 | 0 | 0 | 1448677.286 | 785090.4456 | 2233767.7316 |  | 1453581.27 | 17629779 | 0 | 0 | 0 | 0 | 0 | 0 | 19083360.27 | 19083360.27
Rangeview Ogden Feeder Main Phase 2 | Ogden Feeder Main | Water | Linear Extension | Active | Design | Class 5 | 2027+ | Construction expected to begin 2023. Split project out from Ogden Feeder Main Phase 1 to show different phases in new Bylaw | [10 empty] | 2027: 6250000; 2028: 6250000 | 12500000 | 12500000
Lower Sarcee Feeder Main | Lower Sarcee Feeder Main | Water | Linear Extension | Active | Design | Part 1 - Class 1 Part 2 - Class 3 | 2022 | Construction underway with expected completion mid-2022. Project is broken into two parts. | 30900000 | 30855000 |  | 67774.3463 | 49216.7025 | 118902.2549 | 1577220.9579 | 6710230.1762 | 8523344.4378 |  | 3654991.54 | 21394000 | 1250000 | 0 | 0 | 0 | 0 | 0 | 26298991.54 | 26298991.54
210 Ave SW Pump Station | 210 Ave SW Pump Station | Water | Facility | Active | Design | Class 2 | 2023 | Timing of the project was delayed. | 15000000 | 14980000 |  | 77930.8028 | 0 | 40957.6929 | 22903.822 | 909400.2225 | 1051192.5402 |  | 810241.03 | 7416000 | 11570000 | 0 | 0 | 0 | 0 | 0 | 19796241.03 | 19796241.03
Northridge FM Ph 1 and 2 | Northridge FM Ph 1 and 2 | Water | Linear Extension | Active | Construction | Class 1 (Phase I Only) | Phase 1 2020 Phase 2 Unknown | Project split into 2 line items (below) for greater clarity | 30700000 | 30747000 | 0 | 2786.8768 | 449080.1526 | 3984646.99 | 27893371.5431 |  | 32329885.5626 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Northridge FM Ph 1 (some completed in 2018) | Northridge FM Ph 1 and 2 | Water | Linear Extension | Active | Construction | Actuals + Class 1 (for future portions) | Dec. 2021 | Construction of Feedermain complete, anticipate infrastructure will be in service Q4, 2021. | 30700000 | 30747000 |  | 2787.3788 | 449080.3415 | 3984646.8327 | 27893371.5431 | 8890128.9898 | 41220015.0859 |  | 932294.38 | 253706 | 0 | 0 | 0 | 0 | 0 | 0 | 1186000.38 | 1186000.38
Northridge FM Ph 2 | Northridge FM Ph 1 and 2 | Water | Linear Extension | Hold | Hold | Class 5 | 2027+ | Phase 2 on Hold | [10 empty] | 2027: 16600000; 2028: 16600000 | 33200000 | 33200000
Northridge Reservoir Land | Northridge Reservoir Land | Water | Land | Hold | Design | Class 5 | 2025 or beyond | Timing deferred. Not needed at this time for early Phases of Glacier Ridge. Land purchase not likely before 2022. | 3200000 | 0 | 17293.56 | 131907.3165 | 663.323 | 0 | 0 | 0 | 149864.1994 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Northridge Reservoir | Northridge Reservoir | Water | Facility | Hold | Hold | Class 5 | Unknown, Likely beyond 2026 | Not needed for initial stages of Glacier Ridge. Dependent upon timing of 14 New Communities. Updated cost projections are for first cell only. | 12100000 | 1354000 | [8 empty] | 2500000 | 0 | 0 | 0 | 13000000 | 0 | 1677000 | 1677000 | 18854000 | 18854000
Northridge West Leg Feedermain (Ph 1 and Ph 2) | North Ridge West Leg Feedermain | Water | Linear Extension | Hold | Feasibility / Scoping | Class 5 | Phase 1 2026 or beyond Phase 2 Unknown | Not needed for initial stages of Glacier Ridge. Dependent upon timing of 14 New Communities. | 20800000 | 9300000 |  | 0 | 0 | 0 | 69145.7136 | 1571.6005 | 70717.3141 |  | 1200000 | 1200000 | 3400000 | 3500000 | 5700000 | 5800000 | 0 | 0 | 20800000 | 20800000
Belvedere Water Feeder Main PH 1 and 2 | Belvedere Water Feeder Main Ph 1 and 2 | Water | Linear Extension | Active | Conceptual Design | Class 4 | 2022 | Preliminary design in progress. | 23000000 | 8800000 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 636435.69 | 19563564 | 0 | 0 | 0 | 0 | 0 | 0 | 20199999.69 | 20199999.69
Providence Starlight East Pump Station (Interim/Ph 1) and Associated Feedermain to LOC Boundary | Providence 146 Ave Feedermain, Starlight East Pump Station and Westview Reservoir and Land | Water | Linear Extension | Active | Feasibility / Scoping | Class 1 | Starlight Phase 1 2022 Others Unknown, likely 2026 or beyond | Interim/Phase 1 servicing only proceeding at this time. Remainder of scope moved to Ultimate/Phase 2 project which is likely not proceeding until beyond 2026. Total cost of full scope will exceed original estimate. It should be noted that this project is linked to Starlight East Pump Station (Ultimate/Phase 2) and that the original 2015 cost estimate as well as Original OSL Rate Estimate did not have 2 separate projects planned. This multi-stage solution has a larger scope than the original solution and will subsequently result in a higher overall cost to the levy. |  |  |  | 0 | 0 | 0 | 390245.2758 | 4059824.3291 | 4450069.6049 |  | 13635417.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13635417.74 | 13635417.74
Starlight East Pump Station (Ultimate/Ph 2) | Providence 146 Ave Feedermain, Starlight East Pump Station and Westview Reservoir and Land | Water | Facility | Active | Design | Class 5 | TBD - 2023/2024 | Ultimate/Phase 2 build out required for full servicing of appproved growth (14NC/27ADC) | 15755000 | 15755000 | [8 empty] | 2027: 11335000; 2028: 11335000 | 22670000 | 22670000
Providence 146 Ave Feedermain | Providence 146 Ave Feedermain, Starlight East Pump Station and Westview Reservoir and Land | Water | Linear Extension | Hold | Hold | Class 5 | 2027+ |  | 5347000 | 1900000 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 697000 | 0 | 0 | 697000 | 697000
Westview Reservoir Land | Providence 146 Ave Feedermain, Starlight East Pump Station and Westview Reservoir and Land | Water | Land | Hold | Hold | Class 4 | 2027+ | Land purchase not likely before 2022, reservoir likely 2027 or beyond | 1100000 | 1100000 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 1100000
Providence Westview Reservoir | Providence 146 Ave Feedermain, Starlight East Pump Station and Westview Reservoir and Land | Water | Facility | Hold | Hold | Class 5 | 2027+ | Land purchase not likely before 2022, reservoir likely 2027 or beyond | 8877000 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 1157850 | 0 | 0 | 1157850 | 1157850
[9 empty] | 272959000 | 181607000 | 17293.56 | 283186.7212 | 948040.5196 | 8129153.7705 | 59440832.4725 | 23040038.851 | 91858545.8949 | 0 | 34739398.37 | 100294447 | 16220000 | 10399000 | 18700000 | 7654850 | 42588000 | 42588000 | 273183695.37 | 273183695.37
New Projects Identified in 2018 Bylaw

## Completed projects
*The data contained within this spreadsheet is shared under an Open Government Licence - City of Calgary. This open government licence only applies to this data and this data only. Terms of Use can be found at https://data.calgary.ca/stories/s/Open-Calgary-Terms-of-Use/u45n-7awa
Project Name (Edited with Brief Description) | Name in 2016 or 2018 Bylaw | Utility | Type | Estimated Construction Completion (substantial) | Project notes - Nov. 18, 2021 | Original 2015 Cost Estimate (Source: Levy Bylaw 2016/2018) Forecasted Total Project Cost (10-Year time Horizon 2015-2024) | Original OSL Rate Estimate (forecasted annual spends 2015-2020) | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Past Actual Spend (2015-2020) | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Cost Projections Total
Sanitary Linear Extension Infrastructure
North Ridge Macdonald Trunk (Ph 2) | North Ridge Macdonald Trunk | Sanitary | Linear Extension | Complete | FAC Issued 2018. Project complete. | 7100000 | 7138000 | 4258567.7 | 259844.4075 | 0 | 0 | 0 | 0 | 4518412.1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
West Pine Creek Sanitary Trunk Ph 2 | West Pine Creek Sanitary Trunk Ph 2 | Sanitary | Linear Extension | Complete | Project complete | 46600000 | 46308000 | 1319159.93 | 11198025.0811 | 23649066.4824 | 7288548.49 | 294501.9318 | 0 | 43749301.9154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 Ave NE San Trunk | 144 Ave NE San Trunk | Sanitary | Linear Extension | Complete | Project complete. A portion of this project has been handed back to The City to construct. | 24100000 | 24130000 | 903515.07 | 6858372.9025 | 232545.9167 | 0 | 0 | 144.179 | 7994578.0683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North Beddington San Ph 2 CFA | North Beddington San Ph 2 CFA | Sanitary | Linear Extension | Complete | Project complete | 8900000 | 8888000 | 561637.56 | 4257282.2082 | 308706.7535 | 0 | 0 | 988.3786 | 5128614.9002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Beddington Creek II East Leg | Beddington Creek II East Leg | Sanitary | Linear Extension | Complete | Project complete | 2700000 | 2728000 | 197438.85 | 0 | 0 | 0 | 39586.3139 | 0 | 237025.1639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Haskayne Sanitary Trunk | Haskayne Sanitary Trunk | Sanitary | Linear Extension | Complete - currently in maintenance period | Construction Agreement has been executed. More progress in 2019 than orignially projected. Project substantially complete and is currently in the maintenance period. | 3900000 | 3900000 |  | 0 | 0 | 0 | 866415.557 | 724145.5038 | 1590561.0608 | 99920 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 124920
Water Linear Extension Infrastructure
210 Ave Feeder Main | 210 Ave Feeder Main | Water | Linear Extension | Complete | Project complete | 12000000 | 11784000 | 780546.23 | 1153056.8489 | 11048531.3621 | 970808.2837 | 9262.796 | 0 | 13962205.5207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
East McKenzie FM | East McKenzie FM | Water | Linear Extension | Complete | Project complete | 6400000 | 6411000 | 4922949.01 | 745868.0045 | 30643.1763 | 23085.6487 | 1506.6819 | 1751.8414 | 5725804.3627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Haskayne Feedermain | Haskayne Feedermain | Water | Linear Extension | Complete - currently in maintenance period | CA has been executed. CCC to be issued upon deficiencies being addressed. | 11300000 | 11300000 |  | 0 | 0 | 0 | 2115346.9568 | 5439774.7884 | 7555121.7452 | 1915580.14 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 1940580.14
[6 empty] | 123000000 | 122587000 | 12943814.35 | 24472449.4527 | 35269493.691 | 8282442.4223 | 3326620.2375 | 6166804.6912 | 90461624.8448 | 2015500.14 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 2065500.14