## Sheet1
*The data contained within this spreadsheet is shared under an Open Government Licence - City of Calgary. This open government licence only applies to this data and this data only. Terms of Use can be found at https://data.calgary.ca/stories/s/Open-Calgary-Terms-of-Use/u45n-7awa | [12 empty] | Cost Projection
Project Name | Growth % | Greenfield % | Established % | Regional % | Utility | Type | Current Project / Budget Activity Status (November 2021) | Current Detailed Status (November 2021) | Current Cost Projection Classification | Estimated Construction Completion (substantial) | Project notes - Nov. 18, 2021 | Current estimate (November 2021) | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Infrastructure
Top Hill Feedermain - Phase 1 | 100% | 100% | 0% | 0% | Water | Extension | Active | Scoping/Feasibility | Class 5 | TBD | Project creates redundancy to support increased growth in the Big Hill East pressure zone. This is only Phase 1 of the project which is required between 2021-2029 to support growth in the 14NC and 27ADC | Phase 1 only - $25.5M | Cost Projection 2022: 12750000; Cost Projection 2023: 12750000
Mountain View Pump STN027 | 100% | 100% | 0% | 0% | Water | Facility - upgrade | Active | Scoping/Feasibility | Class 5 | TBD | Project required for growth and redundancy which supports the 14NC and 27ADC in the Top Hill pressure zone. High-level estimate only at this time. | $1.5M | Cost Projection 2022: 750000; Cost Projection 2023: 750000
Valley Ridge Pump STN041 | 100% | 100% | 0% | 0% | Water | Facility - upgrade | Active | Scoping/Feasibility | Class 5 | TBD | Required for growth in Crestmont pressure zone | $6M | Cost Projection 2022: 3000000; Cost Projection 2023: 3000000
Valley Ridge Feedermains | 80% | 80% | 20% | 0% | Water | Extension | Active | Scoping/Feasibility | Class 5 | TBD | This FM will support growth in the Crestmont pressure zones. In order for this to be functional Valley Ridge Pump STN041 needs to be included. | $23.9M | Cost Projection 2022: 11950000; Cost Projection 2023: 11950000
Glenmore High Lift (Pump Station) | 100% | 50% | 50% | 0 | Water | Facility - Upgrade (adding a new pump) | Active | Scoping/Feasibility | Class 5 | TBD | Required for growth in the Glenmore zone. High-level estimate at this time. | $3M | Cost Projection 2022: 1500000; Cost Projection 2023: 1500000
Beddington (Reservoir) | TBD | TBD | TBD | TBD | Water | Facility - Upgrade | Active | Scoping/Feasibility | TBD | TBD | This project is related to the option investigation underway for the North Calgary Water Servicing Strategy (NCWSS) which will have a direct impact on what is required. At this time, there is insufficient information available to determine the cost. | TBD | Cost Projection 2022: TBD; Cost Projection 2023: TBD
Cranston Santiary Trunk | TBD | TBD | TBD | TBD | Wastewater | Extension | On hold | Scoping/Feasibility |  | On hold | Supports growth in the 14NC and 27ADC | $4M | Cost Projection 2022: 2000000; Cost Projection 2023: 2000000
Chestermere 17 AV Water Meter Chamber (Relocation) | 100% | 50% | 0 | 50% | Water | Facility - Extension | Active | Scoping/Feasibility | Class 5 | 2022 |  | $0.5M | Cost Projection 2022: 250000; Cost Projection 2023: 250000